## Project Info
CSIS 2430 — Project One Plan
1) Project Information
Course / Term | CSIS 2430
Project | Project 1
Team Name | Team Awesome Sauce
Start Date | 2026-02-02
Due Date | 2026-03-01
Checkpoint Date (mid-project) | 2026-02-22
2) Team & Roles (assigned for this project)
Roles are assigned per project and rotate between projects.
Team Member | Role (Implementation / Verification / Communications) | Primary Responsibilities (1–2 bullets) | Availability / Notes
Noah Kolling | Implementation Lead | Owns core algorithm implementation; integrates modules; maintains main branch health. | Every night after 5pm when available
Benjamin Paul | Verification Lead | Creates test plan; edge cases; validates outputs; documents verification evidence.
Nelson Long | Communications Lead | Assembles report/video; ensures run instructions; tracks deliverables; merges documentation.
3) Repository & Access (Required for Projects 1–4)
Platform | GitHub
Repository URL | https://github.com/Ben1078/cs-2430-project1
Instructor invited as viewer by checkpoint? | Yes — invited 2026-02-04
Repo Structure Requirement (summary) | UML, ReadMe, Design Notes
Task Tracking (Jira) | https://cs2430-team-awesome-sauce.atlassian.net/jira/software/projects/P1/boards/1

## Milestones
4) Milestones (Timeline)
Define 4–6 milestones. Each milestone has a definition of done. Status: NS / IP / D.
Milestone | Target Date | Owner | Definition of Done | Status (NS/IP/D) | Evidence Link / Pointer
Repo set up + skeleton running | 2026-02-18 | Ben | Repo created; README run steps; sample I/O runs. | D | PR #1 (setup)
Core implementation complete | 2026-02-24 | Noah | All required features implemented; compiles/runs end-to-end. | IP | Branch: feature/core
Verification complete | 2026-02-27 | Ben | Test suite covers edge cases; expected vs actual documented. | NS
Report/video draft complete | 2026-02-28 | Nelson | Draft report sections complete; video outline + script notes. | NS
Final integration + submission | 2026-03-01 | Nelson | All deliverables finalized; tags release; submission package ready. | NS

## Tasks
Jira
Issue key | Summary | Status | Due date | Assignee | Updated | Description
P1-20 | Implement class methods | To Do | 22/Feb/26 12:00 AM | Noah | 22/Feb/26 8:41 PM
P1-19 | Submit Checkpoint 2 | To Do |  |  | 22/Feb/26 6:49 PM
P1-18 | Create Repository +baseline ReadMe/run steps | Done | 22/Feb/26 12:00 AM | Benjamin Paul | 23/Feb/26 3:48 AM
P1-17 | Final Polish | To Do | 22/Feb/26 12:00 AM |  | 23/Feb/26 3:28 AM
P1-16 | Report Draft | To Do | 22/Feb/26 12:00 AM | Nelson Long | 23/Feb/26 3:47 AM
P1-15 | Checkpoint Package | To Do | 22/Feb/26 12:00 AM |  | 22/Feb/26 6:40 PM
P1-14 | Design Notes: Assumptions, invariants, tradeoffs | To Do | 22/Feb/26 12:00 AM |  | 22/Feb/26 6:40 PM
P1-13 | Implement Edge Case Tests + Expected Outputs | To Do | 22/Feb/26 12:00 AM | Benjamin Paul | 23/Feb/26 4:07 AM
P1-12 | Define verification plan | To Do | 22/Feb/26 12:00 AM | Benjamin Paul | 23/Feb/26 4:07 AM
P1-11 | implement core data structures and parsing | To Do | 22/Feb/26 12:00 AM |  | 23/Feb/26 3:28 AM
P1-10 | Draft UML/module diagram in /docs | In Progress | 22/Feb/26 12:00 AM |  | 23/Feb/26 3:48 AM
P1-9 | Create Project Plan | In Progress | 22/Feb/26 12:00 AM | Nelson Long | 23/Feb/26 3:48 AM
P1-8 | Submit checkpoint One | In Progress |  |  | 22/Feb/26 8:37 PM
P1-7 | Create Test Cases | To Do |  | Benjamin Paul | 23/Feb/26 4:07 AM
P1-6 | Create Basic Pseudocode | In Progress | 22/Feb/26 12:00 AM | Noah | 22/Feb/26 7:29 PM
P1-5 | Prepare IntelliJ IDE Integration with GIT | Done | 22/Feb/26 12:00 AM | Nelson Long | 23/Feb/26 4:07 AM | Setup the GIT integration and connect to the project Github.
P1-1 | Prepare Coding Environments in IntelliJ | Done | 22/Feb/26 12:00 AM | Nelson Long | 23/Feb/26 4:07 AM | We have decided to use IntelliJ to work on Project 1. Everyone should download it and get familiar with the IDE.

## Verification Plan
6) Verification Plan (Verification Lead owns this section)

## Risks
7) Risks / Blockers
Risk / Blocker | Impact | Mitigation Plan | Owner | Status

## Updates
8) Update Log (Required: at least 2 per project)
Date | Summary of Update (what changed / what completed) | Blockers / Resolutions | Link(s)
2026-02-18 | Repo created; First Meeting and plan session. | None. | https://docs.google.com/document/d/1CFXl3qpKwwma6qjmA5W9Mtzn6xMdZotbPeOrCE_9ZnM/edit?tab=t.0
2026-02-22 | Github created and started, pseudocode finished; JIRA board created | Minor merge conflict resolved via PR review. | https://github.com/Ben1078/cs-2430-project1
2026-02-23 | Docs folder created; readme.md created | N/A | docs/ Readme.md